## Sheet1
Dissertation Task/Activity | Type | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Administration & Writing Activities
Plan & Write Project Proposal | ADMN | September W2: Proposal
Research Ethics Checklist & Submission | ADMN | September W4: Research Ethics
Plan & Write Interim Report | ADMN | November W1: Interim Report
Plan & Write Dissertation | ADMN | December W2: Planning/Drafting; February W1: Writing Dissertation
Record & Edit Video Demonstration | ADMN | March W1: Demo Video
Plan & Prepare Live Demonstration | ADMN | March W1: Plan Demo
LSEPI Consideration & Deliberation | ADMN | November W1: LSEPI; January W1: LSEPI
Syntax, CFG & Language Development
Research Exisitng Programming Languages | RSRH | September W1: Syntax Research
Feature Design & Deliberation | DSGN | September W2: Feature Design
Finalization of Syntax Design | DSGN | September W4: Syntax Design
Creation of the LL(1) Context-Free-Grammar | CREA | October W2: C.F.G